## Blad1
Datum - 2016 | Wat | description | wie doet wat: | sjors | jelle | iwan | cas | frans
2016-03-02 | planning maken
2016-03-09 | basic world, character, enemies | character that can walk around and hit the enemies |  | corruption | sprites | enemies | character, movement | world design
2016-03-16 | core prototype af | the world is pretty complete some sprites might be missing ,basic corruption,enemies&combat
2016-03-23
2016-03-30 | deadline 2.3 (prototype)
2016-04-05 | deadline 2.4
2016-04-13 | deadline 2.5